## Case
Improving the Human Condition (through better drugs)
A recent addition to the Human Genome Project database makes it clear that a new
and effective drug can be developed to treat certain rare types of male baldness.
Your research team estimates that it would take about 10 months to complete the
research needed to be ready to apply for a patent on the drug. Research would cost
about $100,000 per month, and the actual time required is somewhat uncertain:
They advise you that you should view the actual time required as being normally
distributed, with one standard-deviation's-worth of uncertainty being about 20% of the
estimated required time.
They also point out that your main competitor - the only other firm positioned to do
R&D on this drug - has a lab already in place that they could use for their own
project. This would save them some setup work, and shorten their expected
time-to-patent-application by about 2 months. In all other ways, their costs and
uncertainties would mirror your own. Since time-to-completion varies according to
particular "lucky" or "unlucky" breaks in the research process, it's reasonable to
assume that their actual time-to-completion varies independently of yours.
Assuming that, with their lab in place, the competitor is certain to initiate an R&D
effort, should you? In net present value terms, holding the patent would be worth
about $3,000,000. You will wrap up your research program as soon as either you or
your competitor files for a patent.
|  | cost per month | 100000
|  | value of success | 3000000
|  |  | Us | Them
|  | expected duration | 10 | 8 | (months)
|  | uncertainty | 2 | 1.6 | (months)
|  |  | Simulation |  |  | These are "live" cells. Each time you
|  | actual duration | 11.0866 | 9.1156 | (months) | press "F9", the spreadsheet will
|  | profit | -911561.3531 | 2088438.6469 |  | recalculate, and new simulated
|  | we win? (yes/no = 1/0) | 0% |  |  | durations will appear.
|  | profit if we win (0 otherwise) | 0
I've used KSim (the "Kellogg simulation" package used extensively in my
probability course) to estimate our expected profit if we enter the race.
$E$35 | $E$36 | $E$37 | monitored cell
-109370.2599 | 21.97% | 485560.4717 | mean
1239333.3749 | 41.4% | 917611.9626 | sample standard deviation
-1358898.5429 | 0% | 0 | minimum
2830784.1284 | 100% | 2830784.1284 | maximum
100000 | 100000 | 100000 | number of simulation runs
7681.4678 | 0.2566% | 5687.4179 | margin of error (95% confidence)
With a sample size of 100,000 observations, we estimate our expected profit
from entering the race to be substantially negative: -$109,370.
One standard-deviation's-worth of variability in our actual profit is (estimated to be)
$1,239,333. This uncertainty arises because, on upside, the roughly 22% of the time
we win the race, we have a couple of million dollars in net profit, while, on the downside,
the 78% of the time we lose, we end up hundreds of thousands of dollars in the hole.
How much can we trust our estimate of our expected profit? We can be
95%-confident that it differs from our true expected profit by no more than
$7,681. And we can be equally confident that our estimate of the chance of
winning the race differs from our true chance by no more than 0.26%.
The final column in the simulation output can help us break out some (estimated) details.
| 21.97% | Pr(we win)
| 2210106.8355 | E[net profit ¦ we win]
| 78.03% | Pr(we lose)
| -762438.4617 | E[net profit ¦ we lose]
If, through an additional upfront expenditure of resources, we could cut the expected
duration of the project (for our scientific staff) to only 9 months, could it be worth our
while to spend those resources?
Changing Cell E30 (our expected duration) to 9, and then rerunning the simulation:
$E$35 | $E$36 | monitored cell
268533.8624 | 33.81% | mean
1419962.9762 | 47.31% | sample standard deviation
-1281932.9329 | 0% | minimum
2886267.8014 | 100% | maximum
100000 | 100000 | number of simulation runs
8801.0217 | 0.2932% | margin of error (95% confidence)
Our chance of winning would rise to roughly 34%, and our expected net profit would
rise to a positive level: approximately $268,534. Comparing this expectation to the
required upfront expenditure will guide our decision.